## Sheet1
Task | When?
Arrange a gathering for you and your parents. | 9 to 12 months
Determine budget and how expenses will be shared. | 9 to 12 months
Discuss the size, style, location, and scope of the wedding you want. | 9 to 12 months
Choose a target wedding date and time. (The actual date will depend on venue availability.) | 9 to 12 months
Create a binder to store and organize ideas, worksheets, receipts, brochures, etc. | 9 to 12 months
Visit and reserve wedding and reception sites. | 9 to 12 months
Meet with your officiant. | 9 to 12 months
Start compiling your guest list to estimate head count. Consider budget when thinking about “must-invites” versus “nice-to-invites.” | 9 to 12 months
Begin shopping for the wedding gown. | 9 to 12 months
Choose the members of your wedding party. | 6 to 9 months
Enroll in wedding/shower gift registries. | 6 to 9 months
Hire a photographer and a videographer. | 6 to 9 months
Book an engagement photo session, especially if you plan to include a professional engagement picture with Save-the-Date cards. | 6 to 9 months
Hire a caterer. | 6 to 9 months
Hire a florist. | 6 to 9 months
Make arrangements for music to be played at the ceremony and reception. | 6 to 9 months
(Tasks might include booking a band or solo musician, hiring a DJ, choosing significant musical selections, and so on.). | 6 to 9 months
Reserve a block of hotel rooms for out-of-town guests. (Ask about group rates.) | 6 to 9 months
Send out Save-the-Date cards. (Include lodging info and maps, as possible.) | 6 to 9 months
Shop for wedding rings. | 6 to 9 months
Select and order wedding gown, leaving ample time for delivery and alterations. | 6 to 9 months
Shop for bridesmaids’ dresses. | 6 to 9 months
Schedule wedding cake design appointments and tastings. | 6 to 9 months
Start planning your honeymoon. | 6 to 9 months
Finalize the guest list. | 4 to 6 months
Order invitations (25 extra) and other wedding stationery (i.e., place cards and thank you notes). | 4 to 6 months
Plan wedding-day beauty preparations; ask your stylist how far in advance they book wedding parties, and whether they are willing to work on the wedding site. | 4 to 6 months
Finalize all honeymoon plans. If traveling outside the country, arrange for visas, passports and inoculations. | 4 to 6 months
Hire your wedding day transportation (carriage, limousine service, etc.). | 4 to 6 months
Plan the rehearsal dinner. | 4 to 6 months
Obtain a marriage license. Bring all necessary documents. | 2 to 4 months
Order tuxedoes for the groom and groomsmen. | 2 to 4 months
Meet with the caterer to go over menus, wine selections, etc. | 2 to 4 months
Order the wedding cake. | 2 to 4 months
Order your wedding rings. | 2 to 4 months
Confirm wedding ceremony and reception music. | 2 to 4 months
Book a hotel room for the wedding night. | 2 to 4 months
If you plan on writing your own vows, start writing them now. | 2 to 4 months
Mail the wedding invitations 8 weeks before your wedding date. | 4 to 8 weeks
Do a hair and makeup run-through (including wedding veil, if applicable). | 4 to 8 weeks
Confirm all transportation plans. | 4 to 8 weeks
Work on seating arrangements for the reception. | 2 to 4 weeks
Finalize arrangements for out of town attendants and guests. | 2 to 4 weeks
Confirm details with the photographer, florist, and other vendors. | 2 to 4 weeks
Have final fitting for bridal gown and bridesmaids’ dresses. | 2 to 4 weeks
Write your rehearsal dinner toast. | 2 to 4 weeks
Purchase gifts for the wedding attendants. | 2 to 4 weeks
Compile a list of all of the wedding vendors and wedding party, with contact information. Carry this list with you everywhere you go (just in case). | 2 to 4 weeks
Communicate rehearsal dinner details to those who will attend the rehearsal and rehearsal dinner. | 2 to 4 weeks
Look into where bride, groom and attendants will dress for the ceremony. | 2 to 4 weeks
Enclose any fees due on the wedding day in envelopes for easy distribution. | 1 week
Give the caterer a final head count. | 1 week
Appoint a trustworthy person to bring important items (cake knife, toasting glasses, etc.) to the reception. | 1 week
Appoint someone to act as an “organizer” to handle any last-minute problems. | 1 week
Review final details for those in the wedding party. | 1 week
Get final beauty treatments (manicure, facial, massage, waxing, brow shaping, etc.) | 1 week