## Sample Calculations
Project Risk Assessment Template - Sample
Project Sample #1
Risk Probability/Impact | Number of Risks | Impact Factor | Risk Score
High-High | 7 | 5 | 35
High-Medium | 4 | 4 | 16
High-Low | 10 | 2 | 20
Medium-High | 6 | 4 | 24
Medium-Medium | 9 | 3 | 27
Medium-Low | 12 | 1 | 12
Low-High | 13 | 3 | 39
Low-Medium | 18 | 1 | 18 | Risk Calculation Table
Low-Low | 22 | 0 | 0
|  |  |  | 0-1 | Low Risk
Total Number of Risks | 101 |  |  | 1-2 | Medium Risk
Total Risk Score |  |  | 191 | 2-3 | Medium/High Risk
|  |  |  | 3+ | High Risk
Risk Factor (Risk Score/Number of Risks) |  |  | 1.8911
A medium level of risk for the project
Project Sample #2
Risk Probability/Impact | Number of Risks | Impact Factor | Risk Score
High-High | 27 | 5 | 135
High-Medium | 35 | 4 | 140
High-Low | 10 | 2 | 20
Medium-High | 9 | 4 | 36
Medium-Medium | 9 | 3 | 27
Medium-Low | 22 | 1 | 22
Low-High | 15 | 3 | 45
Low-Medium | 18 | 1 | 18 | Risk Calculation Table
Low-Low | 22 | 0 | 0
|  |  |  | 0-1 | Low Risk
Total Number of Risks | 167 |  |  | 1-2 | Medium Risk
Total Risk Score |  |  | 443 | 2-3 | Medium/High Risk
|  |  |  | 3+ | High Risk
Risk Factor (Risk Score/Number of Risks) |  |  | 2.6527
A medium/high level of risk for the project

## Instructions
Project Risk Assessment Template - Instructions
1) Count the number of risks you have identified for your project, based on impact and probability. Your count will yield the number of high probability/high impact risks (high/high), high probability/medium impact risks (high/medium) and so on
2) Input the figures for each probability/impact combination in column B of the spreadsheet
3) The spreadsheet will calculate the total number of risks and the total risk score, which is the number of each type of risk multiplied by the impact factor in column C
Note: It is not recommended to change the impact factor. But, if you do so, understand that it will alter the calculations for an overall high, medium or low risk project. If you change the impact factor you should change the risk calculation table that indicates the overall risk for the project
4) Look at the risk factor score (cell E19 and E37 in the samples) to determine the overall risk factor. Compare that result with the Risk Calculation Table to determine the overall risk of your project
5) As a general rule, any project scoring an overall medium/high or high risk level should focus on risk reduction before execution.