## Project Requirements Checklist
Project Requirements Checklist
From the LinkedIn Learning course Project Management Foundations: Requirements
Activity | Start | Finish | Status
Identify standards.
Prepare the elicitation plan.
Identify and analyze stakeholders.
Collect requirements.
Analyze requirement attributes.
Prioritize requirements.
Create use cases.
Document the requirements.
Validate the requirements.
Manage changes to requirements.

## Relevant Standards
Relevant Standards
From the LinkedIn Learning course Project Management Foundations: Requirements
Issuer | Number | Name | Date
ISO | ISO 21500 | Guidance on Project Management
DLA | MIL-STD-961E | Defense and Program-Unique Specifications Format and Content
ISO/IEC/IEEE | 29148-2018 | Systems and software engineering – Life cycle processes – Requirements engineering

## Requirements Elicitation Plan
Requirements Elicitation Plan
From the LinkedIn Learning course Project Management Foundations: Requirements
Stakeholder | Elicitation Technique | Interviewer/Facilitator/Analyst | Participants/Representatives
Project sponsor | Interview
Account managers | Group session
Customer service staff | Observation
Technical support staff | Process documentation
Small customers | Online survey
Large customers | RDAW

## Project Stakeholders
Project Stakeholders
From the LinkedIn Learning course Project Management Foundations: Requirements
Stakeholder ID | Stakeholder | Position | Influence | Impact
1 | Sponsor | Advocate | 10 | 3
2 | Finance team | Advocate | 8 | 1
3 | IT team | Opponent | 3 | 7
4 | Large customers | Advocate | 3 | 8
5 | Small customers | Opponent | 3 | 10

## Requirements – Attributes
Project Requirements / Attributes
From the LinkedIn Learning course Project Management Foundations: Requirements
ID | Description | Complexity | Risk | Author | Source | Owner | Urgency | Priority | State | Stability
1 | When a user presses the "off" button, the machine will shut down. | Easy | Low | Darrell | Interview with Donna on 12/15 | Gabe | High | High | Drafted | High
2
3
4
5
6
7
8
9
10

## Change Log (Track Attributes)
Project Requirements Change Log
From the LinkedIn Learning course Project Management Foundations: Requirements
ID | Description | Approved On
1 | Removed requirement #4 | 2019-01-06
2
3
4
5
6
7
8
9
10